## DECA
Delivery Environment Complexity Analytic (DECA)
Project name
Date
Evaluation panel members
Rating
Factor | Low (Level 1 Complexity) | 1 Low | 2 Med | 3 High | High (Level 3 Complexity) | Reason for rating | Strategies to address risks associated with medium and high ratings
Strategic importance | Low priority operational level project. Expected benefits are necessary but low in value relative to organisation’s/government’s overall ambitions. Externally there is little political, media or public interest and failure would not have significant impact outside the organisation. |  | 1 |  | Critical to delivery of policy, key strategic objectives or legal obligations, with very high expectation of benefits. High level political or public interest with strong media attention. Failure would have major impacts and consequences outside the organisation.
Stakeholders/Influencers | Low number of stakeholders or level of influence. Stakeholders are aligned with the business objectives, supporting the project and agreeing on the expected outcomes. Key stakeholders and influencers are unlikely to change. |  | 1 |  | Significant number of stakeholders with high levels of influence and differing or misaligned objectives/expectations. Stakeholders/influencers may change.
Requirements and benefit articulation | Requirements and expected benefits are clear and linked to business policy. Key performance measurements link to goals, vision and values. |  |  | 1 | Ambiguity around requirements and how the expected benefits contribute to the realisation of the goals, vision and values. High uncertainty on project impact.
Stability of overall context | Requirements, governance and delivery modes are clear and unlikely to change. No significant risk of change in scope, structure, external requirements or economic/political landscapes. High degree of confidence in planning, estimates and/or governance. Necessary approvals/investment already received or guaranteed. |  | 1 |  | High risk of scope, structure, external requirements or economic/political landscapes changing. Low level of certainty within key estimates, planning and/or governance. Uncertainty over whether necessary authorisations will be received.
Financial impact and value for money | Investment is not significant relative to sponsoring body’s capital expenditure, or comparable investments. Project is not material to key suppliers. Anticipated revenues, efficiencies or returns on investment are not fundamental to the business. High level of assurance over key estimates. |  |  | 1 | Investment is significant for the sponsoring body. Investment expected to deliver significant value for money, efficiencies or returns. Highly involved type/source of investment anticipated. Low level of assurance over key estimates.
Execution complexity (including technology) | No new or untested business practices or technologies form part of the scope. There is front end loading for phased implementation and piloting if required. Organisation or its partners has past experience of all practices, key technologies and methods used. |  |  | 1 | New/untested business practices or technology is required. Wide scope and challenging objectives with limited scope for risk management such as phased implementation or piloting due to immovable deadlines and demanding targets.
Interfaces / Relationships | Project spans few boundaries (organisational, political, regional) and success is not dependent on relationships. Governance is not complex and supports decision-making and reporting. Success is not dependent on factors outside control of the organisation. |  |  | 1 | Project spans many boundaries with internal and external partners. Success is dependent on factors mainly outside control of the organisation and is dependent relationship management. Governance is complex.
Range of disciplines and skills | Delivery involves few specialist disciplines or skill requirements. Acquiring the skills for implementation is straightforward and readily available in the market. |  | 1 |  | Large number of disciplines and skills and/or potential for strain on the supply chain capacity and capability.
Dependencies | Project is not critical to the delivery of other projects. |  | 1 |  | Project is critical to the delivery of other projects.
Extent of change | Business as usual. | 1 |  |  | Large amount of organisational change required to deliver desired outcomes and benefits. Delivery represents a fundamental change to the organisation.
Organisational capability: performance to date | Demonstrated capability to deliver project through delivery of similar successful projects. Culture promotes ‘intelligent client’ attributes. |  |  | 1 | Has not demonstrated key capabilities in delivering major projects and/or has not delivered under similar arrangements in the past.
Interconnectedness | Consideration of the required alignment and relationships between policy, culture, practices, technology, people, processes and procedures. Inter-relationships inform decision-making and risk management. |  | 1 |  | Consideration of the relationships between policy, culture, practices, technology, people, processes and procedure has not been investigated, captured or communicated.
Source: UK HM Treasury. Improving Delivery: Project Initiation Routemap. Delivery Environment Complexity Assessment (DECA) tool.