## Delivery model evaluation
Procurement delivery model evaluation tool
Project name
Date
Evaluation panel members
Delivery model:
Options evaluation criteria (and considerations) | Criteria weight % | Traditional |  | Design and build |  | Package based |  | Direct managed |  | Alliance |  | Public private partnership |  | Early contractor involvement |  | Panel of suppliers
|  | Score | Weighted score | Score | Weighted score | Score | Weighted score | Score | Weighted score | Score | Weighted score | Score | Weighted score | Score | Weighted score | Score | Weighted score
Time: Is early completion required? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Certainty of time: Is project completion on time critical to operations? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Certain of cost: Is a firm price needed before any commitment to construction given? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Price competition: What is the relative importance of price versus quality in determining the degree of price competition? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Flexibility: Are variations necessary or possible after work has begun on-site? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Complexity: Does the building need to be highly specialised, technologically advanced or highly serviced? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Quality: Is high quality of the product, in terms of material and workmanship and design concept, important? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Responsibility: Is the client willing to take design risk, or does the single point of responsibility for design and construction need to be with the contractor? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Risk: What is the project risk profile, and how are these risks to be allocated and managed - time, cost, quality, health and safety? |  |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 0% |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Note on B8: Enter the weightings that reflect the relative importance of each of the key evaluation criteria established for the project.
Note on D9: Review how well each delivery model is able to meet the key evaluation criteria to help determine the most appropriate model. Score on a scale of 1-5 (5 being most likey to achieve a specific objective, and 1 being least likely).