## Guidance
Essential Task Register
Introduction and guidance
1. Essential task register overview This Essential Task Register (ETR) is designed to provide a blueprint of activities for organisations to cover contract management due diligence and build a Supplier Relationship Management (SRM) strategy. This tool assumes you've already segmented your suppliers into tiers. Guidance on how to do this is at https://www.procurement.govt.nz/guides/guide-to-procurement/manage-the-contract/introduction-to-supplier-relationship-management/ Sections 1 & 2: These two sections provide a programme of activities which, for the purposes of Government Procurement Rule 35, constitute a contract management plan for lower tier (Tier 3 & 4) contracts. This is explained in further detail under 'Process overview' below. 2. Process overview Step 1- Contract & Performance Management Activities This register has been designed to be worked through in numerical order for any contract. This means that section 1 is the starting point of any supplier engagement. Most contracts will require at least some of the activities listed in this section. If a tier requires the activity, it is highlighted in pale red. **Important note** The list of activities in Sections 1 & 2 constitute a basic contract management plan for the purposes of Government Procurement Rule 35, for Tier 3 & 4 suppliers only. Tier 1 & 2 suppliers will need a more thorough/formal Contract Management Plan document. A template for this can be found on the NZGP website. Step 2 - SRM activities SRM activities begin on the right of the bold line with Section 3: Risk Management Activities. As you progress throughout the sections, the more complex the SRM activities become, and the more appropriate they are for Tier 1 & 2 suppliers, rather than Tier 3 & 4 suppliers. The register as a whole, with all sections, comprises a thorough SRM strategy for your higher tier (Tier 1 & 2) contracts.

## Essential Task Register
Supplier Relationship and Contract Management
Essential Task Register
Task key:
Not essential
Essential
In progress
Completed and ongoing
|  |  |  | Section 1: Contract Management Activites |  |  |  | Section 2: Performance Management Activities |  |  |  |  | Section 3: Risk Management Activities |  |  |  |  | Section 4: Cost Management Activities |  |  | Section 5: Relationship Management & Development Activities | [5 empty] | Section 6: Value Creation & Innovation Activities |  |  |  | Section 7: Continuous Improvement Activities
|  |  |  | 1.01 | 1.02 | 1.03 | 1.04 | 2.01 | 2.02 | 2.03 | 2.04 | 2.05 | 3.01 | 3.02 | 3.03 | 3.04 | 3.05 | 4.01 | 4.02 | 4.03 | 5.01 | 5.02 | 5.03 | 5.04 | 5.05 | 5.06 | 6.01 | 6.02 | 6.03 | 6.04 | 7.01 | 7.02 | 7.03
Category | Supplier | Tier | General Notes | Ensure that contracts, variations and supporting documentation (commercial memos etc.) are stored appropriately. | Familiarise yourself with the contractual obligations and monitor these. | Manage contract changes effectively by following the contract change process (e.g. catalogue change process). | Conduct annual contract reviews with the supplier. | Validate contracts to ensure that SLAs are present, unambiguous, and still aligned to the contract purpose. | Ensure that measurement and reporting routines are set up and understood by all parties. | Schedule performance reviews to take place as per contract management plan. | Performance management (if required) should include root cause analysis, problem solving, interim and long-term countermeasures and corrective actions. | Conduct bi-annual checks to ensure products/services are delivered on time and are of the quality required. | Ensure that post-contract award risk mitigation actions have been implemented and are effective. | Ensure that the supplier’s financial stability has been checked in the last twelve months and is satisfactory, and that the supplier holds adequate insurance cover. | Ensure that required Business Continuity Plans are in place. | Create a risk register and validate with internal stakeholders and the supplier. | Schedule and conduct regular risk reviews (standing agenda item). | Position cost reduction as the opportunity to remove 'bad cost' from products and services using techniques such as supply chain analysis and value engineering. | Open Total Cost of Ownership (TCO) dialogue with the supplier and internal stakeholders. | Investigate ways suppliers can assist agencies to buy smarter and leverage the savings opportunities available. | Form strategic supplier management/engagement plan, aligned to the overall category plan. | Form transactional supplier management/engagement plan, aligned to the overall category plan (minimum annual touchpoint for all suppliers, e.g. digital comms) | Appoint senior executives on each side as ‘Executive Relationship Owner’ and set framework to share strategy (e.g. service/product roadmaps), review progress and ensure continuous strategic alignment. | The category lead (SCS) to provide information and support to the Executive Relationship owner wherever necessary. | Ongoing exploration of opportunities to derive more value for both parties from the relationship. | Joint business planning should be created and managed by both parties and be aligned to the strategic category plan. | Identify and engage the relevant stakeholders to develop a guided innovation plan for the supplier (where appropriate). | Facilitate meetings to review innovation opportunities with the supplier and relevant internal stakeholders. | Facilitate discussions related to other value creation opportunities, including topics such as: value enhancement, risk mitigation, time to market, supply chain efficiency, sustainability, investments etc. | Identify stakeholders and the procedure for inviting and processing supplier ideas. | Identify and engage the relevant internal stakeholders to discuss continuous improvement opportunities. | Use performance review forums or regular business reviews to track improvement opportunities. | Create an open dialogue with suppliers to identify ongoing improvement opportunities.
1
2
|  | 3 |  | Section 2: Performance Management Activities 2.01: Simplified SLAs; Section 2: Performance Management Activities 2.05: Annual
|  | 4 |  | Section 2: Performance Management Activities 2.01: Simplified SLAs; Section 2: Performance Management Activities 2.05: Annual
While contract management and supplier relationship management (SRM) have some overlapping functions, the sections on the right of the bold line are typically where contract management activities 'end' and SRM activities begin. The further to the right of the bold line, the more advanced the SRM activities are.